## Sheet1
Team 3 Product Backlog for phase 1 (Analytics Project)
| ITEMS | Effort Required (man hours)
CA1
1 | Understanding Taxi Business | 10
2 | Set Up Database | 10
3 | ETL Pipeline | 10
4 | Data Cleaning & Wrangling | 15
5 | Exploratory Data Analysis in Python | 10
6 | Development of Tableau Dashboard | 15
7 | Presentation & Slides | 10
8 | Project Report + Scrum Docmentation | 20
9 | Buffer Hours (mins of meeting, meeting with supervisor and client) | 5
CA2
10 | Advanced Pre-processing [Feature Engineering / Feature Selection / Outlier Detection / Handle Imbalance] +Scrum Documentation | 35
11 | Modelling | 45
12 | Hyperparameter Tuning | 10
13 | Designing graphics for UI/UX | 25
Total: |  | 220